## Model manipulation
No | Content | Status
1 | Create grid scene in edit website | Done
2 | Create simcity move-control in the scene | Done
3 | Increase size of scene | Done
4 | Add buildings into the scene
5 | Move the building
6 | Rotate a building
7 | Resize a building
8 | Add terrain to scene

## Web Programming
No | Content | Status | Claimed by
1 | Setup the environment | Done | Thang
2 | User profile | Doing | Thang
2.1 | Register | Done | Thang
2.2 | Login | Done | Thang
2.3 | Logout | Done | Thang
2.4 | Reset password | Done | Thang
2.5 | Change password | Done | Thang
3 | User management | Done | Thang
3.1 | List users | Done | Thang
3.2 | Update user info | Done | Thang
4 | Admin send emails to user | Done | Thang
5 | News | Done | Thang
5.1 | News management | Done | Thang
5.2 | Post news | Done | Thang
5.3 | Edit news | Done | Thang
5.4 | Delete/deactivate news | Done | Thang
5.5 | User see news | Done | Thang
6 | User building models
6.1 | List user building models
6.2 | Upload building model
6.3 | Delete a building model
7 | User scenario management
7.1 | List user scenario
7.2 | Edit owned scenario
7.3 | View scenario
7.4 | Clone a scenario
7.5 | Delete owned scenario
8 | Suggestions
9 | Base scenario management
10 | Suggestions management